## Slide 1: KCDC Speed Management Plan (Part B: Implementation 2024-27)
13/02/2025

## Slide 2: Briefing purpose
  Confirm process for implementing Part B (SMP) – Schools
  Confirm the effect on individual schools following October 2024 Briefing
  (Reflects Land Transport Rule: Setting of Speed Limits 2024)
            (the ‘Rule’ - operable 10/24)

## Slide 3: 2023 SMP RECAP
October 2023
  Speed Management Plan approved
June 2024 – SMP Implementation Plan, Part A (Completed)
  13 schools – New 30km/h Variable Speed Limit (VSL) signs
  7 roads – New permanent speed limits
  New speed limits - enforceable
2024 to 27 - SMP Implementation Plan, Part B (To be completed)
  Implement 30km/h speed limits
    schools
    towns/ villages

## Slide 4: 2024 Briefing summary (Oct. 24)
Part B: Implementation (Option 5)
  Targets risk (schools)
  Deferred until 2027-30 NLTP
    Paekakariki speed humps (Wellington Rd) excl. RSP outside school
    Waikanae Beach Village speed humps
    Te Horo beach speed humps
    Pedestrian crossing points (Te Moana, Tutere, Mazengarb)
    Mill Road 30km/h permanent speed limit extension
  Withdrawn – 2 sites (not permitted under the ‘Rule’)
    Waikanae Town Centre (Marae Lane, Ngaio Street)
    Raumati South (Poplar Ave)
Includes construction of Te Moana Pedestrian Refuge - east of Nimmo Street West

## Slide 5: 2024 Speed Limits Rule – Key messages
  Roads fronting schools
    30km/h Variable speed limits (not 30km/h permanent)
  Consultation required
    Speed Management Plans
  Consultation NOT required
    30km/h VSL fronting schools
  Funding assistance
    NTLP Dec’ 24 – now possible (application submitted)
  NZTA Certification, either,
    Speed Management Plan
    Alternative Method

## Slide 6: Confirm process
Submit Alternative Method (Not SMP) for remaining schools:
Via Excel template
  NZTA certify – KCDC can then implement
Speed humps/ Raised pedestrian zebra crossings etc
  8 schools
30km/h Variable speed limits
  11 schools
Consultation
No consultation required as per ‘Rule’
Schools invited comment proposals prior to Xmas 2024
Consultation adjacent residents re signs/ speed humps*

## Slide 7: Effects (Changes from Oct. 2024 briefing)
  Paekākāriki –
    2 x Speed humps deferred to 2027 – 30
    Wellington Road raised pedestrian zebra crossing RETAINED
  Te Ra Waldorf
    Pedestrian platform REPLACED with temporary speed hump
  Raumati Beach School
    Raised pedestrian zebra crossing REMOVED (does not qualify)
    30km/h variable SL REPLACES 30km/h permanent
  Kapakapanui School
    Proposed 30km/h VSL EXTENDED
  Te kura-ā-iwi Whakatupuranga Rua Mano
    Raised threshold REPLACED with Speed hump
    30km/h variable SL REPLACES 30km/h permanent
  Te Kura Kaupapa Māori o te Rito
    30km/h variable SL REPLACES 30km/h permanent

## Slide 8: Next Steps
  February – KCDC submit alternative Method to NZTA*
  March/ April - NZTA Certify Alternative Method
  1st half 2025
    Targeted consultation
      Package 1 - 30km/h VSL signs
      Package 2 - RSP’s/ speed humps/ speed cushions
    Design commences
      Package 1
      Package 2
    Construction of Te Moana Road Pedestrian Refuge
  Late 2025/ early 2026 – Package 1 (Install)
  1st half 2026 – Package 2 (Construct)

## Slide 9
Ron Minnema
Transport Safety Lead
Te kaitaataki Waka Whakaruru
Ron.minnema@kapiticoast.govt.nz

## Slide 10: APPENDIX: MAPS