| TRAFFIC MANAGEMENT PLAN (TMP) – FULL FORM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Use this form for complex activities. Refer to the NZ Transport Agency’s Traffic control devices manual, part 8 Code of practice for temporary traffic management (CoPTTM), section E, appendix A for a guide on how to complete each field. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organisations /TMP reference |  | TMP reference: Add the RCA’s and contractor’s reference number |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor (Working space): State the name of the contractor responsible for the working space |  |  |  |  |  |  |  |  |  |  |  |  | Principal (Client): State the name of the principal or client for this project (eg NZTA or Chorus) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor (TTM): State the name of the contractor responsible for the TTM |  |  |  |  |  |  |  |  |  |  |  |  | RCA: State the name of the RCA who controls the road that the worksite will be on. Note: There can be more than one RCA. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Location details and road characteristics |  | Road names and suburb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | House no./RPs (from and to) |  |  |  |  |  |  |  |  |  |  |  |  |  | Road level |  |  |  |  |  | Permanent speed |  |  |  |
|  |  | Include the road name/s and any affected intersections. Also include the suburb |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Enter house numbers, route positions or power pole numbers where applicable |  |  |  |  |  |  |  |  |  |  |  |  |  | Enter RCA designation |  |  |  |  |  | Enter highest permanent limit |  |  |  |
|  |  | As above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  | As above |  |  |  |
| Traffic details (main route) |  | AADT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Peak flows |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Include AADT where available. The RCA or engineer must provide this information if available. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Include peak hour and heavy vehicle counts where available. The RCA or engineer must provide this information if available. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description of work activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Briefly provide an accurate and complete description of the work or activity eg repairs to median barrier |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Planned work programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Start date |  |  |  |  |  |  | Enter earliest date activity may start |  |  |  |  |  |  |  |  |  | Time |  | Enter earliest time activity may start |  |  |  | End date |  |  |  |  |  |  |  |  | Enter latest date activity may finish allowing for unforeseen issues |  |  |  |  |  |  |  |  |  |  |  | Time |  |  | Enter latest time activity may finish allowing for unforeseen issues |  |  |  |  |  |
| Consider significant stages, for example: - road closures - detours - no activity periods. |  |  |  |  |  |  | Provide details of any significant stages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Alternative dates if activity delayed |  |  |  |  |  |  | For larger activities, identify any alternative dates that can be scheduled if the work is delayed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Road aspects affected (delete either Yes or No to show which aspects are affected) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Pedestrians affected? |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  | Property access affected? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  | Traffic lanes affected? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |
| Cyclists affected? |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  | Restricted parking affected? |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  | Delays or queuing likely? |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |
| Use the ‘Aspects affected’ field to identify how the activity will affect the road. These effects will need to be covered in the layout drawings/TMDs or later in your TMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed traffic management methods |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Installation (includes parking of plant and materials storage) |  |  |  |  |  |  |  |  | Provide full description of all installation procedures for operations that involve TTM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Attended (day) |  |  |  |  |  |  |  |  | Provide full description of all procedures for operations that involve TTM or impact upon TTM for operation where the activity is underway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Attended (night) |  |  |  |  |  |  |  |  | Provide full description of all procedures for operations that involve TTM or impact upon TTM for operation where the activity is underway Provide details of night overhead lighting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unattended (day) |  |  |  |  |  |  |  |  | Provide full description of all procedures for operations that involve TTM or impact upon TTM for operation where the activity is incomplete but there is a hazardous situation remaining that requires TTM to protect road users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unattended (night) |  |  |  |  |  |  |  |  | Provide full description of all procedures for operations that involve TTM or impact upon TTM for operation where the activity is incomplete but there is a hazardous situation remaining that requires TTM to protect road users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Detour route |  |  |  |  |  |  |  |  | Include details of the route of the detour (provide a map if detour is complex) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Does detour route go into another RCA’s roading network? Yes No (delete either Yes or No) If Yes, has confirmation of acceptance been requested from that RCA? Yes No (delete either Yes or No) Note: Confirmation of acceptance from affected RCA must be submitted prior to occupying the site. If the detour transfers road users to another RCA’s roading network, request confirmation of acceptance from that RCA. The confirmation of acceptance from affected RCA must be submitted prior to occupying the site. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Removal |  |  |  |  |  |  |  |  | Provide full description of all removal procedures for operations that involve TTM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Proposed TSLs (see TSL decision matrix for guidance) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | TSL details as required Approval of Temporary Speed Limits (TSL) are in terms of Section 6 of Land Transport Rule: Setting of Speed Limits 2017, Rule 54001/2017 (List speed, length and location) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Times (From and to) |  |  |  |  |  |  |  |  | Dates (Start and finish) |  |  |  |  |  |  |  |  |  |  |  | Diagram ref. no.s (Layout drawings or traffic management diagrams) |  |  |  |  |  |  |  |
| Attended day/night | A temporary maximum speed limit of km/h is hereby fixed for motor vehicles travelling over the length of m situated between (House no./RP) and (House no./RP) on (street or road name) If a TSL is appropriate, add the TSL details - temporary speed (eg 70km/h), approximate length (eg 200m) and the location (eg RP 01N-0260/0.50 or 23-53 Chews Lane). Add additional rows into this section if required. Note: When the worksite is set up, the actual location of the TSL signs will need to be recorded on the on-site record or the equivalent company sheet that records the same information. For legal purposes (eg speed enforcement), this information must be retained for 12 months and be provided on request. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Include the hours that the activity will take place Note: Activity hours may be restricted by the RCA or contract documents. |  |  |  |  |  |  |  |  | Add the date or date range for this activity |  |  |  |  |  |  |  |  |  |  |  | List the reference for either: - the site specific layout drawing(s) that are attached to the TMP (eg layout drawing 1, 2), or - the appropriate traffic management diagram(s) from the TTM handbook, if worksite is on a level LV or level 1 road where the RCA has approved the use of generic TMDs. |  |  |  |  |  |  |  |
| Unattended day/night | A temporary maximum speed limit of km/h is hereby fixed for motor vehicles travelling over the length of m situated between (House no./RP) and (House no./RP) on (street or road name) As above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |
| TSL duration | Will the TSL be required for longer than 12 months? If yes, attach the completed checklist from section I-18: Guidance on TMP Monitoring Processes for TSLs to this TMP. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No Delete either Yes or No to indicate whether the TSL will be required for longer than 12 months. If yes, attach the completed checklist from section I-18 |  |  |  |  |  |  |  |
| Positive traffic management measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Refer to section C10.1.1 Positive traffic management measures must be used when installing TSLs of: - less than 70km/h in areas with permanent posted speed limits of 100km/h, or - less than 50km/h in areas with a permanent posted speed limit of 70 or 80km/h. Detail the extent of positive traffic management to be undertaken when: - temporary speed restrictions below 70km/h in areas with existing permanent speed limits of 100km/h, or below 50km/h in areas with existing permanent speed limits of 70km/h or 80km/h, or less than 30km/h in a 50km/h area - traffic is stopped to allow work to proceed - traffic is reduced to one lane. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contingency plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Generic contingencies for: - major incidents - incidents - pre planed detours. Remove any options which do not apply to your job |  |  |  |  |  |  |  | Record the contingencies for the worksite. Consider the items listed and add or amend as required. Also add additional contingencies appropriate to the worksite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Major Incident A major incident is described as: - Fatality or notifiable injury - real or potential - Significant property damage, or - Emergency services (police, fire, etc) require access or control of the site. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actions The STMS must immediately conduct the following: - stop all activity and traffic movement - secure the site to prevent (further) injury or damage - contact the appropriate emergency authorities - render first aid if competent and able to do so - notify the RCA representative and / or the engineer - under the guidance of the officer in charge of the site, reduce effects of TTM on the road or remove the activity if safe to do so - re-establish TTM and traffic movements when advised by emergency authorities that it is safe to do so - Comply with any obligation to notify WorkSafe. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Incident An incident is described as: - excessive delays - real or potential - minor or non-inquiry accident that has the potential to affect traffic flow - structural failure of the road. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actions The STMS must immediately conduct the following: - stop all activity and traffic movement if required - secure the site to prevent the prospect of injury or further damage - notify the RCA representative and / or the engineer - STMS to implement a plan to safely remove TTM and to establish normal traffic flow if safe to do so - re-establish TTM and traffic movements when it is safe to do so and when traffic volumes have reduced. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Detour If because of the on-site activity it will not be possible to remove or reduce the effects of TTM once it is established a detour route must be designed. This is likely for: - excessive delays when using an alternating flow design for TTM - redirecting one direction of flow and / or - total road closure and redirection of traffic until such time that traffic volumes reduce and tailbacks have been cleared. The risks in the type of work being undertaken, the risks inherent in the detour, the probable duration of closure and availability and suitability of detour routes need to be considered. The detour and route must be designed including: - pre- approval form the RCA’s whose roads will be used or affected by the detour route - ensure that TTM equipment for the detour - signs etc are on site an pre-installed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Actions When it is necessary to implement the pre-planned detour the STMS must immediately undertake the following: - Notify the RCA and / or the engineer when the detour is to be established - Drive through the detour in both directions to check that it is stable and safe - Remove the detour as soon as it practicable and safe to do so and the traffic volumes have reduced and tailbacks have cleared - Notify the RCA and / or the engineer when the detour has been disestablished and normal traffic flows have resumed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | Note also the requirements for no interference at an accident scene: In the event of an accident involving serious harm the STMS must ensure that nothing, including TTM equipment, is removed or disturbed and any wreckage article or thing must not be disturbed or interfered with, except to: - save a life of, prevent harm to or relieve the suffering of any person, or - make the site safe or to minimise the risk of a further accident; or - maintain the access of the general public to an essential service or utility, or - prevent serious damage to or serious loss of property, or - follow the direction of a constable acting in his or her duties or act with the permission of an inspector. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Other contingencies to be identified by the applicant (i.e. steel plates to quickly cover excavations) |  |  |  |  |  |  |  | Add additional contingencies appropriate to the worksite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Authorisations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Parking restriction(s) alteration authority |  |  |  |  |  | Will controlled street parking be affected? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  | Has approval been granted? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  |  |  |  |  |  | If no approval has been granted, make application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Authorisation to work at permanent traffic signal sites |  |  |  |  |  | Will portable traffic signals be used or permanent traffic signals be changed? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  | Has approval been granted? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  |  |  |  |  |  | If no approval has been granted, make application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Road closure authorisation(s) |  |  |  |  |  | Will full carriageway closure continue for more than 5 minutes (or other RCA stipulated time)? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  | Has approval been granted? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  |  |  |  |  |  | If no approval has been granted, make application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Bus stop relocation(s) – closure(s) |  |  |  |  |  | Will bus stop(s) be obstructed by the activity? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |  |  |  |  |  | Has approval been granted? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No |  |  |  |  |
|  |  |  |  |  |  | Required where a bus stop/s is obstructed by activity. If no approval has been granted, make application |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Authorisation to use portable traffic signals |  |  |  |  |  |  |  |  |  |  |  |  | Make, model and description/number |  |  |  |  | Include make, model and description number of the portable traffic signals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | NZTA compliant? |  |  |  |  | Yes No (delete either Yes or No) Confirm that the signals are approved for use by the NZTA. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EED |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is an EED applicable? |  |  |  |  |  |  |  |  |  |  |  | Yes No (delete either Yes or No) Indicate if an EED has been agreed for this worksite |  |  |  |  |  | EED attached? |  |  |  | Yes If yes then attach the EED to the TMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Delay calculations/trial plan to determine potential extent of delays |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Required where potential delays may occur. RCA will define when these are required once draft plan is submitted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public notification plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Required where activity may cause disruption to community. RCA to define when these are required Include details of notices proposed to be advertised via local radio or newspapers or distributed to local residents. Refer contract documentation and RCA requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Public notification plan attached? |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No (delete either Yes or No) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| On-site monitoring plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Attended (day and/or night) |  |  |  |  |  |  |  |  |  |  | Identify the frequency of monitoring the continued effectiveness of the traffic management measures Detail the monitoring of attended and unattended worksites both overnight and during weekends or holiday breaks For example, at an attended static worksite with the STMS or TC on-site, the inspection frequency may be: - 2 hourly for signs, portable channelling and delineation devices and arrow boards - Daily for cleanliness of safety garments, non-portable equipment and flashing beacons on vehicles - Continuously for wearing of safety jackets. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Unattended (day and/or night) |  |  |  |  |  |  |  |  |  |  | This field must be completed for any unattended sites On unattended worksites (overnight, weekends etc,) the STMS assesses the needs of that site and includes details of monitoring in the TMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Method for recording daily site TTM activity (eg CoPTTM on-site record) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| State how on-site TTM activity will be recorded. This could be the CoPTTM on-site record or the equivalent company document provided it covers the following information: - details of the STMS who is in charge of the worksite (name, qualification, ID and expiry date of qualification) - If worksite delegated to a TC (level 1) or STMS-NP (only on limited level 2 worksites), details of the TC/STMS-NP who is in charge of the worksite (name, qualification, ID and expiry date of qualification) - the worksite monitoring including: - site set-up - 2-hourly monitoring - site removal - details of any TSLs installed: - date installed - time installed - placement (RPs or street numbers) - length of TSL (in metres) - date removed - time removed. If using a company on-site record instead of the CoPTTM on-site record, you must attach that document to the TMP. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site safety measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| In this section include special items such as overhead lighting for night time MTC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Temporary safety barrier system |  |  |  |  |  | Will a temporary safety barrier system be used at this worksite? |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No Indicate appropriate answer |  |  |  |  |  |  |  | If yes, has the temporary safety barrier system been designed by an installation designer and independently reviewed as being fit for purpose? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No Indicate appropriate answer |  |  |  |  |
|  |  |  |  |  |  | Statement from temporary safety barrier installation designer attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Attached Not attached Indicate appropriate answer |  |  |  |  |
| Other information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Further details may be required as a result of specific site conditions or contractual requirements. In addition, TMPs should also include the following as appropriate: - liaison with emergency services and public transport operators (if they could be affected by the worksite) - changes to parking controls - traffic environment details of speed limit, parking, traffic signals, pedestrian crossings, road alignment and hierarchy - specialised equipment such as pilot vehicles, use of temporary traffic signals - materials storage - pedestrian barriers and equipment to be used - queuing - plant operational requirements, eg truck waiting and filling areas. TMPs for mobile operations should also include the following additional information: - the type and function of each vehicle in the mobile operation - the vehicles that will be equipped with attenuators and arrow boards and their location within the worksite - the number, location and, duration of exposure and tasks of personnel who are permitted to leave their vehicles - the method of inter-vehicle communication. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Site specific layout diagrams |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number |  |  |  |  |  |  |  |  |  |  |  |  |  | Title |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Enter applicant diagram number. Also consider whether a layout diagram is required for set-up /removal of the worksite. |  |  |  |  |  |  |  |  |  |  |  |  |  | Enter name of attached diagram |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| As above |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| As above |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| As above |  |  |  |  |  |  |  |  |  |  |  |  |  | As above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact details |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | CoPTTM ID |  |  |  |  |  |  |  |  |  | Qualification |  |  |  |  |  |  |  | Expiry date |  |
| Principal |  |  |  |  |  |  | Organisation named on permit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  | Optional |  |
| TMC |  |  |  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  | Optional |  |
| Engineers’ representative |  |  |  |  |  |  | Detail optional - Independent person employed by engineer whose responsibilities include TTM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  | Optional |  |
| Contractor |  |  |  |  |  |  | State name of the contracting company and the name of their contact person |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  | Optional |  |
| STMS |  |  |  |  |  |  | Name Where multiple names are included in the TMP, the name of the STMS in charge must be written on the On-site record |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  |  |  |  |  |  | Level of qualification |  |  |  |  |  |  |  | Date of expiry |  |
| TC |  |  |  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  |  |  |  |  |  | Level of qualification |  |  |  |  |  |  |  | Date of expiry |  |
| Others as required |  |  |  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 24/7 contact number |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  |  |  | Optional |  |  |  |  |  |  |  | Optional |  |
| TMP preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation |  |  |  | STMS signature |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date prepared |  |  |  |  |  | STMS signature |  |  |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  | Level of qualification |  |  |  |  |  |  | Expiry date |  |  |
|  |  |  |  | Name (STMS qualified) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  |  |  | ID no. |  |  |  |  | Qualification |  |  |  |  |  |  | Expiry date |  |  |
| This TMP meets CoPTTM requirements Number of diagrams attached |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TMP returned for correction (if required) |  |  |  | Name of TMC or engineer returning TMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date accepted |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  |  | Level of qualification |  |  |  |  |  |  | Expiry date |  |  |
|  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  |  | ID no. |  |  |  |  |  | Qualification |  |  |  |  |  |  | Expiry date |  |  |
| Engineer/TMC to complete following section when approval or acceptance required |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Temporary safety barrier system |  |  | The attached temporary road safety barrier design has been independently reviewed as being fit for purpose |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Yes No Not required Indicate appropriate answer |  |  |  |  |  |  |  |  |  |  |
| TMP Approved |  |  |  | Name of person approving TMP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date accepted |  |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  |  | Level of qualification |  |  |  |  |  |  | Expiry date |  |  |
|  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  | ID no. |  |  |  |  |  | Qualification |  |  |  |  |  |  | Expiry date |  |  |
| Acceptance by TMC (only required if TMP approved by engineer) |  |  |  | Name of TMC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date accepted |  |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  | CoPTTM ID number |  |  |  |  |  | Level of qualification |  |  |  |  |  |  | Expiry date |  |  |
|  |  |  |  | Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  | Signature |  |  |  |  |  |  |  |  |  | ID no. |  |  |  |  |  | Qualification |  |  |  |  |  |  | Expiry date |  |  |
| Qualifier for engineer or TMC approval |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approval of this TMP authorises the use of any regulatory signs included in the TMP or attached traffic management diagrams. This TMP is approved on the following basis: - To the best of the approving engineer’s/TMC’s judgment this TMP conforms to the requirements of CoPTTM. - This plan is approved on the basis that the activity, the location and the road environment have been correctly represented by the applicant. Any inaccuracy in the portrayal of this information is the responsibility of the applicant. - The TMP provides so far as is reasonably practicable, a safe and fit for purpose TTM system. - The STMS for the activity is reminded that it is the STMS’s duty to postpone, cancel or modify operations due to the adverse traffic, weather or other conditions that affect the safety of this site. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Notification to TMC prior to occupying worksite/Notification completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of notification to TMC required |  |  |  |  | Describe the notification procedure to be used |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Notification completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  |  |  |  |  | Record date notification was completed |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Time |  |  |  |  |  |  |  |  |  |  | Record time notification was completed |  |  |  |  |  |  |  |  |  |  |  |  |  |